## Task List
Task ID | Owner | Milestone | Title | Weight (0-100] | Start Date and Time | Completed Date and Time | URL | Details | Task ID | Owner | Milestone | Title | Weight (0-100] | Start Date and Time | Completed Date and Time | URL | Details | Task ID | Owner | Milestone | Title | Weight (0-100] | Start Date and Time | Completed Date and Time | URL | Details
1 | Yusuf Emir Yılmaz | Milestone 1 (Design) | Define core classes, types, and method stubs | 30 | 2026-05-16 21:26 | 2026-05-17 01:23 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/ae2b1bda32064997db8db8e2810bc0f0f96aa272 | Define core classes, types, and method stubs
2 | Yusuf Emir Yılmaz | Milestone 1 (Design) | Creating classes in packages | 10 | 2026-05-16 21:32 | 2026-05-16 22:00 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/e5da17a16e8ec45a4935565001ac33c1422aa4ca | Created and organized classes across project packages.
3 | Yusuf Emir Yılmaz | Milestone 1 (Design) | Create UtilityProvider.java | 5 | 2026-05-16 23:00 | 2026-05-16 23:05 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/71f1734153bdd898c139b9c3849fbd8e612bb4d8 | Create UtilityProvider.java
4 | Mustafa Şen | Milestone 1 (Design) | Creating classes, types, and methods. | 25 | 2026-05-16 21:00 | 2026-05-16 21:58 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/c3925510fe9be09903d5d3419bfa8e22bb223b6c | Creating classes, types, and methods, and marking methods with "TODO" to be filled in later."
5 | Mustafa Şen | Milestone 1 (Design) | Creating utilityProvider class. | 40 | 2026-05-16 21:02 | 2026-05-16 23:26 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/40d961fa45a9bfae4fe20842f543acb4e5d607e7 | Creating utilityProvider class, types, and methods, and marking methods with "TODO" to be filled in later."
6 | Mehmet Kerem Saman | Milestone 1 (Design) | Created classes and interfaces | 50 | 16.05.2026 15.30 | 16.05.2026 22:27. | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/a1d9bf7e1590275f4331131abd7d27bcb860e37a
7 | Yusuf Emir Yılmaz | Milestone 1 (Design) | implementing simulator classes and methods wihout body | 15 | 2026-05-16 23:20 | 2026-05-16 23:58 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/442eff112d7e8ea97d65d74d666f88077069b7cc#diff-658d701872636e79d23434332b02f389b3b0ace82d36fef03d16fa43ef7d1165 | Created simulator classes and introduced placeholder method implementations.
8 | Yusuf Emir Yılmaz | Milestone 1 (Design) | Integrate ResourceType into resource producers/consumers and add ResourcePool | 40 | 2026-05-17 18:32 | 2026-05-16 19:40 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/a60fa53c92a948fad583fc8cd8221d1a0803f85e | Integrated ResourceType into resource producers and consumers, and added ResourcePool for centralized resource management.
9 | Mustafa Şen | Milestone 1 (Design) | I added enum. | 5 | 2026-05-16 22:10 | 2026-05-16 22:28 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/327bd1d351987ff83df75418615c0ef63396e210 | I added enum
10 | Mehmet Kerem Saman | Milestone 1 (Design) | Added ServiceType enum | 25 | 16.05.2026 15.30 | 2026-05-16 22:32 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/9b5230c010a5f1eaf6716d1647b0f3ce17de9af7
11 | Mehmet Inci | Milestone 1 (Design) | added the classes defined methods and marked the methods which implement… | 50 | 2026-05-17 18:17 | 17.05.2026 19.23 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/1a7f4471d189cd428d8068a7701ae23c94c2f05e
12 | Umut Berk Şanlı | Milestone 1 (Design) | creating Hospital class and marking methods with TODO to be filled in later | 20 | 2026-05-18 17:41 | 2026-05-18 19:28 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/e3d175c116e70d40bf6c58b7ed59bce2045861cb
13 | Umut Berk Şanlı | Milestone 1 (Design) | creating classes and marking methods with TODO to be filled in later | 25 | 2026-05-18 18:09 | 2026-05-18 20:13 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/2ce9db5ae7e25d45b4aab909605b03b65488f26c
14 | Umut Berk Şanlı | Milestone 2 (Final) | Implement basic structure and level progression in Commercial class | 30 | 2026-05-21 15:17 | 2026-05-21 16:27 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/d62c447787e778d79c3469e947ae4bc6c08127ab
15 | Umut Berk Şanlı | Milestone 2 (Final) | Implement produce method for Commercial class | 20 | 2026-05-21 16:43 | 2026-05-21 17:31 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/567dbe12688aef1f14b48cd1afad7942d027b879
16 | Umut Berk Şanlı | Milestone 2 (Final) | Implement utility and resource demand logic for Commercial class | 30 | 2026-05-21 17:26 | 2026-05-21 18:54 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/db71cc24ef3d919e581357782f2d1a13adf612b0
17 | Mehmet Kerem Saman | Milestone 2 (Final) | Update Zone Class | 25 | 23.05.2026 15.00 | 23.05.2026 19.49 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/fa5fc1fe283f4117e14611cf977c405c661ef5d4
18 | Mehmet Kerem Saman | Milestone 2 (Final) | Implemented recomputeLevel and produce methods in Housing | 30 | 23.05.2026 14.00 | 23.05.2026 20.08 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/491c9562cae7f317261cc673f9b9be2311033e4b
19 | Yusuf Emir Yılmaz | Milestone 2 (Final) | Implemented Commercial zone core logic and resource requirements | 20 | 2026-05-23 20:20 | 2026-05-23 21:20 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/df9c370feec7883a8d2948d3f6f0346e841fa8ae | Implemented the core logic of the Commercial zone, including resource requirement handling and related functionality.
20 | Mehmet Kerem Saman | Milestone 2 (Final) | Implemented Industrial logic and corrected constructor inheritance | 30 | 23.05.2026 14.00 | 23.5.2026 20.08 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/5476621fe4beb2fe13ede1a7b3f23e1ce1345808
21 | Umut Berk Şanlı | Milestone 2 (Final) | fix Commercial.java resource demand and level rules | 30 | 2026-05-24 14:48 | 2026-05-24 15:32 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/85dc9ea510ccc9e63a706833425323a4928f3958
22 | Umut Berk Şanlı | Milestone 2 (Final) | Implemented Cell base class and Position class | 25 | 2026-05-24 17:04 | 2026-05-24 18:16 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/7cc2def2cd1e06258611642e3850ab2f73fc16b7
23 | Yusuf Emir Yılmaz | Milestone 2 (Final) | Implements the core city model and IO output layer for ObjectVille II, and fixes the broken Cell.setPosition() stub to a proper void setter. | 40 | 2026-05-24 19:52 | 2026-05-24 21:40 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/87884df4d6eaea5a28c3971156f28be438032e9c | Implemented the core city model and IO output layer for ObjectVille II while fixing the Cell.setPosition() setter implementation.
24 | Mehmet Inci | Milestone 2 (Final) | implement core logic for position and city grids with distance formulas | 10 | 2026-05-27 19:52 | 2026-05-27 20:28 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/fbd5b0591262ed9b69f6957b0636a48d2475b6b1
25 | Mehmet Inci | Milestone 2 (Final) | i implemented maploader and file parser logic | 50 | 2026-05-27 01:53 | 2026-05-27 02:32 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/98d85a061a35b6ddd3d5fcb6949ff13107cec7a7
26 | Mehmet Inci | Milestone 2 (Final) | I implement utility distribution using BFS routing | 50 | 2026-05-30 06:32 | 2026-05-30 08:45 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/b4d354fd38540bac362fdd1a6f41325493c0b783
27 | Mustafa Şen | Milestone 2 (Final) | I filled the Simulator class . | 60 | 2026-05-30 18:48 | 2026-05-30 20:28 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/7b8cd56d4d7e9b270bfc91a562f0d8c00e1d172d | I filled the Simulator class this class has many
28 | Mustafa Şen | Milestone 2 (Final) | I created Main class and filled it. | 40 | 2026-06-01 21:20 | 2026-06-01 23:50 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/fcce5a14f8dd0f90fe108f1f4add586d359e3367 | I created Main class and filled it.
29 | Mehmet Kerem Saman | Milestone 2 (Final) | I fixed Zone , Housing and Industrial Classes | 25 | 23.05.2026 14.00 | 04.06.2026 18.30 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/b9a5d4233528fdd977e641b926f97d8a0d1a42eb
30 | Yusuf Emir Yılmaz | Milestone 2 (Final) | Fix MapLoader to handle maps without a dimension header Fix utility distribution and service logging in Simulator Fix Commercial zone level-up logic | 15 | 2026-06-04 15:23 | 2026-06-04 16:15 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/2c5cc23b5eb69fc094cdb1caeff6a3ce6fb75ef4 | Resolved issues in MapLoader, utility distribution, service logging, and Commercial zone level-up behavior.
31 | Yusuf Emir Yılmaz | Milestone 2 (Final) | Rewrite utility distribution as layered BFS with column-major ordering and replace loops with lambdas | 15 | 2026-06-04 16:16 | 2026-06-04 17:25 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/2840baa9fb4e6fab9eb30bb0f4cfa5022754db33 | Refactored the utility distribution system by implementing a layered BFS traversal strategy and adopting column-major ordering. Replaced traditional loops with lambda-based iterations to improve readability, maintainability, and code consistency while preserving the original distribution behavior.
32 | Umut Berk Şanlı | Milestone 2 (Final) | Fix Industrial and Commercial level requirements | 5 | 2026-06-05 20:47 | 2026-06-05 21:24 | https://github.com/ysfeylmz/SE116-AsteroxTeam/commit/ef5c21d4c96f2a11a00d24759753506f571b3fd1

## Developer List
Developer | Number of Tasks | Total Weight | Score | Team Average
Yusuf Emir Yılmaz | 9 | 190 | 43 | 445
Mehmet Kerem Saman | 6 | 185 | 42
Umut Berk Şanlı | 7 | 185 | 42
Mehmet İnci | 4 | 160 | 36
Mustafa Şen | 5 | 170 | 38
0
0
0
0
0